## Read ME
Please READ before using this register
Dear User, thank you for using my template. Please overwrite the existing sample entries in the register
1) | Before using this template go to the sheet "Configuration" and make adjustments in accordance with your project.
2) | Only cells in BLUE FONT COLOR on the sheet "Register" require data-entry. Do not overwrite cells in BLACK FONT, they contain formulas or functions.
3) | To add a new line (dataset) to the register either start typing in the first empty cell immediately under the last entry, or select any cell in the last row and press the TAB-key until a new line is added automatically. Formulas/functions and formatting will be copied down automatically.
4) | To add a new line (dataset) to the register either start typing in the first empty cell immediately under the last entry, or select any cell in the last row and press the TAB-key until a new line is added automatically.
5) | You downloaded this sheet free of charge from
http: project-management.magt.biz
You may use this sheet for your personal use and projects. However, selling the sheet is strictly prohibited.

## Register
Project | [Project Name] | [6 empty] | Duration Tracker
Phase | [Sub-Project or Phase]
Client | [Client] | [6 empty] | Project Mngr.: | [Project Manager] |  |  |  | Last Updated: | 2018-07-06
Client's Repr. | [Client's Representative]
Contractor | [Contractor]
Sub-Contr. | [Sub Contractor]
Task Description |  |  |  |  | Initial Planned Duration |  |  | Revised Planned Duration |  |  | Actual Duration |  |  | Notes
Task ID | Deadline | Task/Work Package | Description/Activities | Task Owner | Planned Start | Planned Finish | Planned Duration (workdays) | Revised Start | Revised Finish | Revised Duration (workdays) | Actual Start | Actual Finish | Actual Duration (workdays) | Remarks
A0815 | 2018-08-20 | Foundations Bldg. A | Excavate, blind, install rebar, install formwork, pour concrete, remove formworks, cure concrete, waterproof, backfill |  | 2018-07-01 | 2018-08-15 | 39 | 2018-07-03 | 2018-08-14 | 37 | 2018-07-02 |  | 6
Formulas:
Planned Duration (workdays) = IF(AND(Register[Planned Start]>0,Register[Planned Finish]=""),"",NETWORKDAYS.INTL(Register[Planned Start],Register[Planned Finish],Workweek[Workweek],Holidays[Date]))
Revised Duration (workdays) = IF(AND(Register[Revised Start]>0,Register[Revised Finish]=""),"",NETWORKDAYS.INTL(Register[Revised Start],Register[Revised Finish],Workweek[Workweek],Holidays[Date]))

## Configuration
Date | Holiday | Workweek
2018-01-01 | New Year | 11
2018-03-30 | Good Friday
2018-04-02 | Easter Monday
2018-05-01 | Labour Day
2018-06-01 | Madaraka Day
2018-06-15 | Eid Al Fitr
2018-10-10 | Moi Day
2018-10-20 | Mashujaa Day
2018-12-12 | Jamhuri Day
2018-12-25 | Christmas Day
2018-12-26 | Boxing Day
1 or omitted = Saturday, Sunday
2 = Sunday, Monday
3 = Monday, Tuesday
4 = Tuesday, Wednesday
5 = Wednesday, Thursday
6 = Thursday, Friday
7 = Friday, Saturday
11 = Sunday only
12 = Monday only
13 = Tuesday only
14 = Wednesday only
15 = Thursday only
16 = Friday only
17 = Saturday only
Note on A1: Marc Arnecke, PMP: List all holidays and other planned periods when work will be discontinued.