## Read me
Please READ before using this register
1) | Dear User, thank you for using my template. Please overwrite the existing sample entries in the register
2) | In case you are using different mix designs, use separate register for each mix-design.
3) | Only cells in BLUE FONT COLOR on the sheet "Register" require data-entry. Do not overwrite cells in BLACK FONT, they contain formulas or functions.
4) | To avoid typing mistakes resulting in incorrect filter results, the entries in the column "Supplier" are restricted. To modify supplier names change entries on the sheet "Validation" before you start making entries. You may add more suppliers over time, however, avoid deleting previous suppliers that delivered you earlier, but not anymore at present.
5) | To add a new line (dataset) to the register either start typing in the first empty cell immediately under the last entry, or select any cell in the last row and press the TAB-key until a new line is added automatically.
6) | On the sheet "Total QTYs" only enter the start date in the first line of the table. Everything else will update automatically.

## Register
Project | [Project Name] | [10 empty] | Concrete Pouring Register
Sub-Project or Phase | [Sub-Project or Phase]
Client | [Client] | [10 empty] | Project Mngr.: |  | [Proj. Mngr.] |  |  |  |  | Printed on: |  | 2018-06-25
Client's Representative | [Client's Representative] | [10 empty] | QA/QC Mngr.: |  | [QA/QC Mngr.] |  |  |  |  | Standard Deviation |  | 0.75
Contractor | [Contractor] | [10 empty] | Mix Design: |  | [Mix-Design]
[12 empty] | Ref.-No.: |  | [Ref.-No.]
[7 empty] | 7-days test |  |  |  |  | 14-days test |  |  |  |  | 28-days test |  |  |  |  | Result (overall)
Cube ID | No. Cubes | Delivery Note(s) | Supplier | Pour Date | Grade | QTY (m3) | 7d Date | 7d 1 (N/mm2) | 7d 2 (N/mm2) | 7d 3 (N/mm2) | 7d Ø (N/mm2) | 14 d Date | 14d 1 (N/mm2) | 14d 2 (N/mm2) | 14d 3 (N/mm2) | 14d Ø (N/mm2) | 28d Date | 28d 1 (N/mm2) | 28d 2 (N/mm2) | 28d 3 (N/mm2) | Ø (N/mm2) | Result | Cu Sum | Overall x̄ | Distr.
B1-BM-GB-A1:A10 - 29/05/2018 | 9 | 1234, 1235, 1236 | Supplier A | 2018-05-25 | 37 | 19 | 2018-06-01 | 35.1 | 34 | 35.3 | 34.8 | 2018-06-08 | 37.9 | 37.3 | 38.3 | 37.8333 | 2018-06-22 | 34.7 | 36 | 37 | 35.9 | Failed | -1.1 | 35.9 | 1.2979e-05
B2-BM-GB-A1:A10 - 01/01/2015 | 9 | 1237, 1238, 1239 | Supplier B | 2018-05-27 | 37 | 19 | 2018-06-03 | 35.3 | 34.1 | 35.2 | 34.8667 | 2018-06-10 | 38.1 | 37.4 | 38.2 | 37.9 | 2018-06-24 | 39.9 | 39 | 39.8 | 39.5667 | Passed | 2.5667 | 37.7333 | 0.51148
B3-BM-GB-A1:A10 - 01/01/2015 | 9 | 1240, 1241, 1242 | Supplier C | 2018-05-31 | 37 | 19 | 2018-06-07 | 37.5 | 36.2 | 37.1 | 36.9333 | 2018-06-14 | 40.3 | 39.5 | 40.1 | 39.9667 | 2018-06-28 | 40.1 | 40.3 | 39.9 | 40.1 | Passed | 3.1 | 38.5222 | 0.3255
B1-BM-GB-B1:B10 - 01/01/2015 | 9 | 1243, 1244, 1245 | Supplier D | 2018-06-15 | 37 | 19 | 2018-06-22 | 35.7 | 34.3 | 35 | 35 | 2018-06-29 | 38.5 | 37.6 | 38 | 38.0333 | 2018-07-13 | 40.3 | 39.2 | 39.6 | 39.7 | Passed | 2.7 | 38.8167 | 0.47901
B2-BM-GB-B1:B10 - 01/01/2015 | 9 | 1246, 1247, 1248 | Supplier E | 2018-06-15 | 37 | 19 | 2018-06-22 | 35.9 | 34.4 | 34.9 | 35.0667 | 2018-06-29 | 38.7 | 37.7 | 37.9 | 38.1 | 2018-07-13 | 40.5 | 39.3 | 39.5 | 39.7667 | Passed | 2.7667 | 39.0067 | 0.4581
B3-BM-GB-B1:B10 - 01/01/2015 | 9 | 1249, 1250, 1251 | Supplier A | 2018-06-15 | 37 | 19 | 2018-06-22 | 35.1 | 33.5 | 33.8 | 34.1333 | 2018-06-29 | 37.9 | 36.8 | 36.8 | 37.1667 | 2018-07-13 | 39.7 | 38.4 | 38.4 | 38.8333 | Passed | 1.8333 | 38.9778 | 0.41699
B1-BM-GB-C1:C10 - 02/01/2015 | 9 | 1252, 1253, 1254 | Supplier B | 2018-06-15 | 37 | 19 | 2018-06-22 | 36.3 | 34.6 | 34.7 | 35.2 | 2018-06-29 | 39.1 | 37.9 | 37.7 | 38.2333 | 2018-07-13 | 40.9 | 39.5 | 39.3 | 39.9 | Passed | 2.9 | 39.1095 | 0.40915
B2-BM-GB-C1:C10 - 02/01/2015 | 9 | 1255, 1256, 1257 | Supplier C | 2018-06-15 | 37 | 19 | 2018-06-22 | 36.5 | 34.7 | 34.6 | 35.2667 | 2018-06-29 | 39.3 | 38 | 37.6 | 38.3 | 2018-07-13 | 41.1 | 39.6 | 39.2 | 39.9667 | Passed | 2.9667 | 39.2167 | 0.38212
B3-BM-GB-C1:C10 - 02/01/2015 | 9 | 1258, 1259, 1260 | Supplier D | 2018-06-15 | 37 | 19 | 2018-06-22 | 36.7 | 34.8 | 34.5 | 35.3333 | 2018-06-29 | 39.5 | 38.1 | 37.5 | 38.3667 | 2018-07-13 | 41.3 | 39.7 | 39.1 | 40.0333 | Passed | 3.0333 | 39.3074 | 0.35407
B1-BM-SL-A1:C10 - 09/01/2019 | 9 | 1261, 1262, 1263 | Supplier E | 2018-06-15 | 37 | 27 | 2018-06-22 | 38.9 | 36.9 | 36.4 | 37.4 | 2018-06-29 | 41.7 | 40.2 | 39.4 | 40.4333 | 2018-07-13 | 39.1 | 40.7 | 39.6 | 39.8 | Passed | 2.8 | 39.3567 | 0.44666
Note on A9: Marc Arnecke, PMP: Please create a system for the marking of cubes, which allows you to identify cubes and correlate them with portions of your work. An example is provided on sheet "Cube ID".
Note on D9: Marc Arnecke, PMP: You may define the suppliers on sheet "Supplier".
Note on F9: Marc Arnecke, PMP: Please do not mix different grades in a sheet.

## Dashboard
[Ref.-No.]
Total number of cubes |  |  | 90 |  |  |  | Total number of cubes | 90
Concrete QTY m3 |  |  | 198 |  |  |  | Failed | 1
[7 empty] | Passed | 9
Average no. cubes per m3 |  |  |  | 0.45455 |  |  | Percentage failed |  | 11.11%
As of |  |  |  | 2018-06-15 |  |  | As of |  | 2018-07-13
Failed | 1 |  |  |  | As of | 2018-07-13
x̄ | 38.5947 | MPa |  |  | As of | 2018-07-13

## Total QTYs
Project | [Project Name] |  |  |  |  | Total Concrete QTYs
Sub-Project/Phase | [Sub-Project or Phase]
Client | [Client] |  |  |  |  | Project Mngr. | [Proj. Mngr.] |  | Printed on | 2018-06-25
Client's Repres. | [Client's Representative] |  |  |  |  | QA/QC Mngr. | [QA/QC Mngr.]
Contractor | [Contractor] |  |  |  |  | Mix Design | [Mix-Design]
[6 empty] | Ref.-No. | [Ref.-No.]
Period Start | Period End | Consumption This Period | Consumption Cummulative | Supplier A | Supplier B | Supplier C | Supplier D | Supplier E | Remarks
2018-05-01 | 2018-05-31 | 57 | 57 | 19 | 19 | 19 | 0 | 0
2018-06-01 | 2018-06-30 | 141 | 198 | 19 | 19 | 19 | 38 | 46
|  | Total: | 198 | 38 | 38 | 38 | 38 | 46

## Cube ID
Location |  | Area |  | Item |  | Narration |  | This table is technically without function and just provides a sample and some help how to build a cube ID.
B1 | Building 1 | GN | Site/General | CL | Column | A1:B5 | here Gridline A1 - B5
B2 | Building 2 | BM | Basement | GB | Ground Beam | …
B3 | Building 3 | GF | Groundfloor | IB | Intermediate Beam
GN | General | MF | Mezzanine Floor | SL | Slab
|  | F1 | Floor 1 | WA | Wall
…
|  | F11 | Floor 11
|  | RF | Roof
GN

## Validation
Suppliers
Supplier A
Supplier B
Supplier C
Supplier D
Supplier E