## Dutch Brothers Plus
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Comments
Phase 1
Signature of project Charter and financing. | 1d | 2018-10-29 | 2018-10-29 |  |  |  |  | Milestone 1
a. Architectural plans are finished | 4d | 2018-10-30 | 2018-11-02 | 2 | PM
b. Schedule Engineering, Sidewalks, Drainage | 5d | 2018-11-05 | 2018-11-09 | 3 | PrM
c. Landscape modification according to DBP Design | 5d | 2018-11-12 | 2018-11-16 | 4 | Sub-Contr
Procurement of property. | 5d | 2018-11-12 | 2018-11-16 |  | Control |  |  | Milestone 2.
a. Plan Approval by City Building | 5d | 2018-11-19 | 2018-11-23 | 6 | PM
b. All building permits acquired | 5d | 2018-11-26 | 2018-11-30 | 7 | PrM
c. Ground work, Landscaping | 5d | 2018-12-03 | 2018-12-07 | 8 | Contractor
d. Construction Supplies ordered with delivery setup | 5d | 2018-12-03 | 2018-12-07 |  | PrM
e. Foundations, plumbing and electric inspections scheduled | 5d | 2018-12-03 | 2018-12-07 |  | PrM
Phase 2
Deconstruction & foundation work | [7 empty] | Milestone 3. Construction Begins Phase 1
a. Inspections for foundation, plumbing and electric performed. | 5d | 2018-12-10 | 2018-12-14 |  | QC & QA
b. Changes made if needed. | 4d | 2018-12-17 | 2018-12-20 | 14 | PM, Contractor
c. Deconstruction of any existing for remodel, install flooring | 4d | 2018-12-18 | 2018-12-21 |  | Contractor
d. Order supplies and set delivery date for next phase. | 5d | 2018-12-17 | 2018-12-21 |  | PrM
e. Set inspection times and dates | 5d | 2018-12-17 | 2018-12-21 |  | PrM
Phase 3
Framing, and electric | [7 empty] | Milestone 4. Construction Begins Phase 2
a. Inspections black top, landscaping, and any changes | 3d | 2019-01-02 | 2019-01-04 |  | QC & QA
b. Framing, and electrical installs, lighting boxes counter tops. | 8d | 2019-01-02 | 2019-01-11 |  | Sub Contractor
c. Order supplies and schedule delivery for next phase. | 5d | 2019-01-07 | 2019-01-11 |  | PrM
d. Schedule framing inspector, electrical inspector, and DBP inspector. | 5d | 2019-01-07 | 2019-01-11 |  | PrM
Stucco, drywall, concrete for landscaping | [7 empty] | Milestone 5. Construction Begins Phase 3
a. Inspections, framing and electrical | 5d | 2019-01-14 | 2019-01-18 |  | QC & QA
b. Make changes if needed. | 6d | 2019-01-16 | 2019-01-23 |  | Contractor
c. Install outside hardy backer, stucco | 5d | 2019-01-21 | 2019-01-25 |  | Contractor
d. Drywall, tape and texture | 5d | 2019-01-21 | 2019-01-25 |  | Sub Contractor
e. Sinks, toilets, tile work lighting assemblies, external lighting. | 5d | 2019-01-28 | 2019-02-01 | 29 | Contractor
f. Order supplies for the next phase schedule delivery date | 5d | 2019-01-28 | 2019-02-01 |  | PrM
g. Schedule inspections for next phase | 5d | 2019-01-28 | 2019-02-01 |  | PrM
Phase 4
Finish Carpentry, Painting, Roofing, Blacktop and signage | [7 empty] | Milestone 6. Construction Begins Phase 4
a. Inspections performed for stucco, insulation, lighting, roof, and plumbing. | 5d | 2019-02-04 | 2019-02-08 |  | QC & QA
b. Make changes if needed. | 6d | 2019-02-06 | 2019-02-13 |  | PM / Contractor
c. Finish Carpentry, Painting, Roofing | 7d | 2019-02-14 | 2019-02-22 | 36 | Contractor
D. Tables Chairs, Point of Sales system, Music Systems, Signage, Alarm Systems, and Blacktop Painting | 5d | 2019-02-18 | 2019-02-22 |  | Sub Contractor
d. Schedule final roof inspections, fire code inspections, and all other final city inspections | 5d | 2019-02-25 | 2019-03-01 | 38 | PrM
e. Schedule DBP deliverable sign-off. | 5d | 2019-02-25 | 2019-03-01 |  | PrM
Phase 5
Walk Through, Sign-off, | [7 empty] | Milestone 7.
a. Inspections--all final. | 10d | 2019-02-25 | 2019-03-08 | 38 | QC & QA & DBP
b. Make changes if needed and reschedule if needed. | 5d | 2019-03-11 | 2019-03-15 | 43 | PM / Contractor
c. DBP & Client inspections | 5d | 2019-03-18 | 2019-03-22 | 44 | QC & QA & PM
e. Deliverable sign-off. | 5d | 2019-03-25 | 2019-03-29 | 45 | PM
Improvement Meeting | 5d | 2019-04-01 | 2019-04-05 | 46 | All Managers